## Budget Actualization
THE ACTION PAINTER · BUDGET ACTUALIZATION
Abarca Entertainment · Proof of Concept · Actualized against the production portal schedule through July 10, 2026
SUMMARY
Original Printed Total (Budget V3 PDF footer) |  |  | 15000 | Hardcoded from the PDF. This number does not match the PDF's own line items.
Actual Sum of PDF's Own Line Items |  |  | 17480 | The PDF footer said $15,000 but its rows sum higher — Set Operations ($2,480) was left out of the printed total.
Corrected Baseline (Camera / Grip / HMU / Boom moved to 3 shoot days) |  |  | 18330 | Production is 3 paid shoot days (Jul 8-10), not 2. This is what V3 should have shipped as.
CONFIRMED WORKING TOTAL (this actualization) |  |  | 18334 | Talent + Crew + Rentals + Set Ops + Misc, actualized against the real schedule and known rates below.
3RD SHOOT-DAY CORRECTION · feeds Corrected Baseline above
Crew Role | Day Rate
Camera Operator | 225
Grip | 200
Hair and Makeup | 200
Boom Operator | 225
Total 3rd-day correction | 850
TALENT
Talent | PDF Days | PDF Rate | PDF Subtotal | Conf. Days | Conf. Rate | Conf. Subtotal | Variance | Notes
Kristine Kay Larsen | 2 | 450 | 900 | 2 | 450 | 900 | 0 | Matches schedule: Jul 8 (Ruth scene) + Jul 10 (Ranch).
Adrienne Janic | 1 | 300 | 300 | 1 | 300 | 300 | 0 | Matches schedule: Jul 9 only (Guardian day).
Joel Berg | 2 | 300 | 600 | 3 | 300 | 900 | 300 | FLAG: budget assumed 2 days. Portal schedule has him Jul 8 (League), Jul 9 (Betty 13A), AND Jul 10 (Ranch) — 3 days. Confirm he's actually being paid the 3rd day rather than it being an unbudgeted gap.
Jake Busey | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0 | Matches: Jul 8 only, courtesy rate, released after.
Hernán Canto | 1 | 250 | 250 | 1 | 250 | 250 | 0 | Matches: Jul 8 only, Workshop scene.
Courtney Ferris | 1 | 150 | 150 | 1 | 150 | 150 | 0 | Matches: Jul 9 only, Betty 13A. (PDF spells this "Farris" — corrected here.)
Carly Durrer | 1 | 140 | 140 | 1 | 140 | 140 | 0 | Matches: Jul 8 only, Ruth scene.
Craig Shoemaker | 1 | 140 | 140 | 1 | 140 | 140 | 0 | Matches: Jul 9 only, Simmons corridor. A stray note briefly had him on Jul 8 too — that was cleaned up in the portal; budget was already right.
TBD Day Player | 1 | 140 | 140 | 1 | 0 | 0 | -140 | RESOLVED: no paid hire. Tony Clark or a crew member already on hand covers the July 8 League/Workshop background — not camera-facing, so no separate day player fee needed. $140 saved. Note: the July 9 Anteroom "aide, voice" role (off-screen line, Sotheby's scene) is a separate need on a different day and is NOT covered by this — still unresolved.
TOTAL TALENT |  |  | 3620 |  |  | 3780 | 160
CREW
Crew Role | PDF Days | PDF Rate | PDF Subtotal | Conf. Days | Conf. Rate | Conf. Subtotal | Variance | Notes
Writer | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Deferred per BCII agreement, recoups on backend.
Director | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Deferred per BCII agreement, recoups on backend.
Editor | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 0 | Cash line item, separate from deferred Director/Writer comp.
Sound Mixer | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0 | Cash line item.
Producer (BCII) | 1 | 0 | 0 | 1 | 0 | 0 | 0 | In-kind, BCII.
Script Supervisor (BCII) | 1 | 0 | 0 | 1 | 0 | 0 | 0 | In-kind, BCII.
Director's Assistant (Lada Mimms) | 2 | 175 | 350 | 2 | 175 | 350 | 0 | RESOLVED: there is no separate First AD — this line is Lada Mimms, Director's Assistant. Unpaid Jul 7 (prep), same as all crew except Norah. Paid Jul 8 and 9 only, which matches the 2 days already budgeted here. No variance.
Hair and Makeup | 2 | 200 | 400 | 3 | 200 | 600 | 200 | Nikolas Belauskas, confirmed Jul 8, 9, 10 (pulled off Jul 7 — he was never actually called that day). 3rd day matches the corrected baseline.
Grip | 2 | 200 | 400 | 3 | 200 | 600 | 200 | Yeva Tamashevich covers Jul 7, 9, 10 at the confirmed $200/day rate. She does not work Jul 8, and the role is not being filled that day — a decision, not an open gap.
PA | 2 | 175 | 350 | 2 | 175 | 350 | 0 | Budgeted 2 days match the still-open Jul 8-9 hire. Isabella Torsitano separately covers Jul 10 as a confirmed crew member — her payment terms aren't specified. If she's paid the same $175/day PA rate, that's a 3rd PA day not yet in this total (+$175). If she's comped, no impact.
Boom Operator | 2 | 225 | 450 | 3 | 225 | 675 | 225 | Jacqueline Martin, confirmed Jul 8, 9, 10. 3rd day matches the corrected baseline.
Camera Operator | 2 | 225 | 450 | 3 | 225 | 675 | 225 | CONFIRMED: Raul self-operates all 3 shoot days, including the Jul 10 Man in Black insert, and is picking up this cost himself — same treatment as Editor and Sound Mixer, real labor billed as a cash line, no ambiguity.
Wardrobe Designer | 22 | 20 | 440 | 22 | 22 | 484 | 44 | Actual rate is $22/hr, not the $20/hr budgeted. 11 of 22 hours logged so far ($242 spent to date). This models full completion at the real rate ($484 total). Rate delta alone is +$44 vs. budget.
BTS | 1 | 0 | 0 | 1 | 0 | 0 | 0 | In-kind, BCII.
Site Manager | 2 | 100 | 200 | 2 | 0 | 0 | -200 | RESOLVED: confirmed in-kind via BCII, matching the portal. The PDF's $200 charge was wrong — zeroed out here.
TOTAL CREW |  |  | 5540 |  |  | 6234 | 694
CAMERA / SOUND RENTALS
Line | PDF Days | PDF Rate | PDF Subtotal | Conf. Days | Conf. Rate | Conf. Subtotal | Variance | Notes
Camera, Lens + Audio | 2 | 1000 | 2000 | 2 | 1000 | 2000 | 0 | Unclear whether this maps to specific days (e.g., a Chuck's Ranch-only rental, since BCII's in-kind camera package likely doesn't leave the lot) or needs a 3rd day like the labor lines above. Confirm which days this actually covers before assuming it's fine as-is.
Lighting Package (BCII) | 1 | 0 | 0 | 1 | 0 | 0 | 0 | In-kind, BCII.
Grip Expendables | 1 | 50 | 50 | 1 | 50 | 50 | 0 | Allowance, unchanged.
TOTAL RENTALS |  |  | 2050 |  |  | 2050 | 0
SET OPERATIONS
Line | PDF Days | PDF Rate | PDF Subtotal | Conf. Days | Conf. Rate | Conf. Subtotal | Variance | Notes
Props | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0 | No actuals reported yet — shown at budget.
Wardrobe (materials) | 1 | 1480 | 1480 | 1 | 1480 | 1480 | 0 | $1,000 of $1,480 spent to date (67.6%), $480 remaining. On pace — shown at full budget since no overage indicated.
TOTAL SET OPERATIONS |  |  | 2480 |  |  | 2480 | 0
MISC
Line | PDF Days | PDF Rate | PDF Subtotal | Conf. Days | Conf. Rate | Conf. Subtotal | Variance | Notes
Crafty & Meals | 1 | 1190 | 1190 | 1 | 1190 | 1190 | 0 | Unchanged — no actuals reported yet.
Gas and Transport | 1 | 600 | 600 | 1 | 600 | 600 | 0 | Unchanged — no actuals reported yet.
Cleanup | 1 | 500 | 500 | 1 | 500 | 500 | 0 | Unchanged — no actuals reported yet.
Insurance | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 0 | Unchanged — no actuals reported yet.
TOTAL MISC |  |  | 3790 |  |  | 3790 | 0
OUTSTANDING OPEN ROLES
Role | Day(s) Needed | Status | [5 empty] | Notes
Grip | Jul 8 |  | RESOLVED | Decision made to go without on Jul 8, not an open hire. Yeva Tamashevich covers Jul 7, 9, 10 only.
PA | Jul 8-9 |  | OPEN | Isabella Torsitano confirmed for Jul 10 only.
Day Player, TBD | Jul 8 |  | RESOLVED | No hire needed — a crew member already on hand covers the aide voice + student background, not camera-facing. $140 saved.
Director's Assistant / First AD | Jul 8-9 |  | RESOLVED | There is no separate First AD. Lada Mimms (Director's Assistant) covers this, paid Jul 8-9, unpaid Jul 7 like other crew.
Camera Operator | All 3 shoot days |  | RESOLVED | Raul self-operates, including the Jul 10 insert, and is picking up the cost himself — same as Editor and Sound Mixer. No hire, no ambiguity.
PENDING BUDGET ITEMS · not yet in the Confirmed Working Total
Item | $ Impact | Direction | [5 empty] | Notes
PA — 3rd day (Isabella, if paid PA rate) | +$175 | Addition | Only if she's paid at the standard PA rate rather than comped.
Prepared July 6, 2026 · Source: Budget V3 PDF + production portal schedule through July 10, 2026. Blue cells are inputs — change them and totals recalculate. Yellow = needs your confirmation. Red = direct conflict between the PDF and the portal.